## Clinic WBS & Timeline
WBS Code | Task | Phase | Start Week | End Week
1.1 | Define goals and scope | Initiation | 1 | 1
1.2 | Feasibility study and risk assessment | Initiation | 1 | 1
2.1 | Stakeholder analysis | Planning | 1 | 1
2.2 | Requirement gathering | Planning | 1 | 1
2.3 | Project charter & approval | Planning | 1 | 1
2.4 | Resource and budget planning | Planning | 1 | 1
3.1 | System architecture design | Design | 2 | 2
3.2 | UI/UX wireframes (Admin, Doctor, Patient) | Design | 2 | 2
3.3 | Database schema design (ERD) | Design | 2 | 2
4.1 | Backend API Development (.NET MVC + SQL) | Development | 3 | 5
4.2 | Frontend – Admin Dashboard (Razor/MVC) | Development | 3 | 5
4.3 | Frontend – Doctor Portal | Development | 3 | 5
4.4 | Frontend – Patient Portal (Booking) | Development | 3 | 5
4.5 | Role-based Authentication & Permissions | Development | 3 | 5
4.6 | Appointment Scheduling Module | Development | 3 | 5
4.7 | Billing & Invoice Module | Development | 3 | 5
4.8 | Notifications (Email/SMS) | Development | 3 | 5
5.1 | Unit testing | Testing | 6 | 6
5.2 | System integration testing | Testing | 6 | 6
5.3 | User Acceptance Testing (UAT) | Testing | 6 | 6
6.1 | Hosting & deployment setup | Deployment | 7 | 7
6.2 | Live environment go-live | Deployment | 7 | 7
7.1 | Admin & Staff Training | Training | 7 | 7
7.2 | Documentation delivery | Training | 7 | 7
8.1 | Bug fixes and updates | Maintenance | 8 | 8
8.2 | Support & feedback integration | Maintenance | 8 | 8